## Sheet1
Project: Backlog Server: tfsapp.dotcom.tesco.org\52_InStoreCustomerPicking Query: Phase1_Bugs List type: Flat
ID | Work Item Type | Testing Impact (Scrum v3) | Title | Assigned To | State | Created Date | Created By
14386 | Bug | 4 - Medium | Sync tray status is updating to status as '2' when the tray sync fails when SIC ON | Renuka Vutukuri | Active | 2016-05-12 08:02 | Renuka Vutukuri
14385 | Bug | 3 - High | Trays are not generated in PickingDB when the deadlock occurs during processing of OutOfSlot Orders | Madhu Bhat | Active | 2016-05-12 07:40 | Murugeswari Tharmaraj
14374 | Bug | 1 - Blocking | Unable to collect the pick trips in NPD when SIC is ON for DCC | Renuka Vutukuri | Active | 2016-05-11 12:57 | Renuka Vutukuri
14364 | Bug | daddsd | GUID's are creating for the wine orders when the SIC flag is ON. | Renuka Vutukuri | Active | 2016-05-11 06:53 | Renuka Vutukuri
14326 | Bug | 2 - Critical | Pick trips download is failing on the buffer logic as Pcs_get requests SP is missing in the latest release. | Anirban Biswas (DOTCOM\ZL52) | Ready for Test | 2016-05-10 07:40 | Renuka Vutukuri
14274 | Bug | 3 - High | One time Script for DCC is not available in Nexus |  | Active | 2016-05-06 17:16 | Akshata Rane
14273 | Bug | 3 - High | Updation of MPAparameters versions is missing in One Time Scripts. |  | Active | 2016-05-06 14:43 | Akshata Rane
14272 | Bug | 1 - Blocking | NPD device is not able to upgrade NPDQueryPickedItem and SupportTools exe’s to the versions on the server due to which it keeps on rebooting | Abhay Prasad | Active | 2016-05-06 14:35 | Akshata Rane
14271 | Bug | 3 - High | One time script for dxsh estate fails for version 20.1.07 | Narayana Shanubhogh | Closed | 2016-05-06 14:12 | Akshata Rane
14250 | Bug | 3 - High | For Substitution Products Of Pre-PickProduct location is Updating as 'Dotcom Area' for Pre-Pick Products After Pre-Picking. | Neema Srivastava | Ready for Test | 2016-05-05 13:13 | Fayaz Ahamed
14243 | Bug | 1 - Blocking | Unable to collect the pick trips in NPD,when SIC is ON. - TrayId not updated in [PickTrip_CustomerDetails] | Nivedita DasSharma | Closed | 2016-05-05 09:05 | Renuka Vutukuri
14238 | Bug | 2 - Critical | Product Location is not getting updated to DotCom Area | Neema Srivastava | Active | 2016-05-05 08:15 | Abhay Prasad
14203 | Bug | 2 - Critical | After Scheduling, Productlocation and Productbarcode data is not getting populated in PickingDb. | Neema Srivastava | Ready for Test | 2016-05-04 09:17 | Abhay Prasad
14199 | Bug | 4 - Medium | Eror in database deployment for version 20.1.06 on GHS9757FSR01 (66.102.14.1 | Narayana Shanubhogh | Closed | 2016-05-04 07:50 | Sumit Gupta
14198 | Bug | 2 - Critical | Duplicate picktrips are creating post SOD when SIC is ON | Renuka Vutukuri | Closed | 2016-05-04 07:13 | Renuka Vutukuri
14164 | Bug | 3 - High | Stop tray functionality fails to trigger because of trolley id is null | Nivedita DasSharma | Closed | 2016-05-03 08:14 | Anirban Biswas (DOTCOM\ZL52)
14163 | Bug | 3 - High | Tray sync is failing - failing to save product location and barcode informtion in Picking DB | Narayana Shanubhogh | Closed | 2016-05-03 08:10 | Anirban Biswas (DOTCOM\ZL52)
14149 | Bug | 2 - Critical | One time scripts for DXSH & Pickingservice throwing errors for DCOS. | Narayana Shanubhogh | Ready for Test | 2016-05-03 05:30 | Sharada Raghunatha
14135 | Bug | 1 - Blocking | None of the Test boxes are configured with Paragon for Scheduling | Shree Harsha | Closed | 2016-05-02 07:58 | Shree Harsha
14134 | Bug | 2 - Critical | GHS_HDSTransfer_Web.msi is missing from the Dev build branch in Nexus | Sajith Balakrishnan | Closed | 2016-05-02 07:52 | Shree Harsha
14133 | Bug | 3 - High | NPD is getting crashed on the CW alert screen, when we have chosen the option ‘Send as closest’ weight for catch weight products. | Renuka Vutukuri | Closed | 2016-05-02 06:53 | Renuka Vutukuri
14132 | Bug | 3 - High | New product location is not getting updated to the productlocationtable when cliked on the misplacedproduct button(SIC-OFF) | Renuka Vutukuri | Ignored | 2016-05-02 06:49 | Renuka Vutukuri
14131 | Bug | 3 - High | PickTrips are not getting created in PickingServiceDB while scheduling | Neema Srivastava | Ready for Test | 2016-05-02 06:39 | shivam sharma
14130 | Bug | 3 - High | ReflectionLoadTypeExceptiona and KeyNotFoundException while referring PickingService.Automation DLL for reusing BDD scenarios | Shree Harsha | Active | 2016-05-02 06:38 | shivam sharma
14093 | Bug | 3 - High | Whenever trays are deleted in PCS, all associated pickingtrips with that pure group are not getting deleted in Picking service DB. | Neema Srivastava | Ready for Test | 2016-04-29 05:53 | Sharada Raghunatha
14092 | Bug | 3 - High | Sync trays is inserting duplicate tray items in pickingservice DB. | Quader Khan (DOTCOM\zd46) | Ready for Test | 2016-04-29 05:50 | Sharada Raghunatha
14069 | Bug | 1 - Blocking | Unable to collect the pickingtrip and could see Ambiguous column name 'PickingTripID' error in the logs for DCOS | Nivedita DasSharma | Ready for Test | 2016-04-28 12:39 | Sharada Raghunatha
14035 | Bug | 3 - High | SIC: Pickingtrip Created time not being populted in DXSH PickingTrip table post download | Likith Vishwanath | Closed | 2016-04-28 04:10 | Likith Vishwanath
14034 | Bug | 3 - High | SIC: PCS_SaveDownloadedPickingTripData has wrong condition while inserting data in Parcel | Likith Vishwanath | Closed | 2016-04-28 04:09 | Likith Vishwanath
14033 | Bug | 3 - High | SIC: SOD is successful even when pickingtrips are not saved in DB | Narayana Shanubhogh | Ready for Test | 2016-04-28 04:09 | Likith Vishwanath
14032 | Bug | 3 - High | SIC: Connection String for DXSH in PickingService DB | Praveen Shankar | Active | 2016-04-28 04:08 | Likith Vishwanath
14031 | Bug | 3 - High | SIC: Onetime Script to populate LabelPrintingArea 2 – Identity column should be removed | Narayana Shanubhogh | Closed | 2016-04-28 04:07 | Likith Vishwanath
14030 | Bug | 3 - High | SIC: ProductSubstitution - We are getting only Rank1 substitutions to Picking DB | Likith Vishwanath | Ready for Test | 2016-04-28 04:06 | Likith Vishwanath
14029 | Bug | 3 - High | SIC: PickingService_Data user does not have permissions on DXSH tables | Likith Vishwanath | Closed | 2016-04-28 04:05 | Likith Vishwanath
14028 | Bug | 3 - High | SIC: RequiresCodeLife check in TrayItem table is set to false by default | Narayana Shanubhogh | Closed | 2016-04-28 04:05 | Likith Vishwanath
14027 | Bug | 3 - High | SIC: CustomerSubstitution Note and Preference column in TrayItem table - needs to be relooked if both the columns are required | Narayana Shanubhogh | Ready for Test | 2016-04-28 04:04 | Likith Vishwanath
14026 | Bug | 3 - High | SIC: Label Printing AreaID not being populated in PickingTrip table of DXSH | Likith Vishwanath | Closed | 2016-04-28 04:04 | Likith Vishwanath
14025 | Bug | 3 - High | SIC: PickingTripID not getting populated in Trolley Tray table | Likith Vishwanath | Closed | 2016-04-28 04:02 | Likith Vishwanath
14024 | Bug | 3 - High | SIC: Create PickingTrip does not work in case of XY ON | Danish Garg | Closed | 2016-04-28 04:01 | Likith Vishwanath
14023 | Bug | 3 - High | SIC: PAV not working as "Duration" is set to zero '0' | Likith Vishwanath | Closed | 2016-04-28 04:00 | Likith Vishwanath
14022 | Bug | 3 - High | SIC: DLL reference issue while creating picking trips in PickingService Microsoft.Practices.EnterpriseLibrary.Common | Likith Vishwanath | Closed | 2016-04-28 03:54 | Likith Vishwanath
13986 | Bug | 3 - High | SIC: Getting 504 error whicle download pickingtrip is triggered(Intermittent) | Likith Vishwanath | Closed | 2016-04-26 12:00 | Likith Vishwanath
13985 | Bug | 3 - High | SIC: Pre Deployment scripts of PickingService DB has create database twice | Narayana Shanubhogh | Closed | 2016-04-26 11:58 | Likith Vishwanath
13984 | Bug | 3 - High | SIC: CodeLife is updating as null incase of RequiredCodeLife parameter set to 0. Which is affecting download pickingtrip | Narayana Shanubhogh | Closed | 2016-04-26 11:57 | Likith Vishwanath
13983 | Bug | 3 - High | SIC: Tiny INT in ProductSubstitution table(PickingServiceDB) to be changed to INT | Nivedita DasSharma | Closed | 2016-04-26 11:55 | Likith Vishwanath
13980 | Bug | 3 - High | Pickingtrip failing to return when partial pick is done. | Humaira Tazyeen | Closed | 2016-04-26 08:20 | Sharada Raghunatha
13934 | Bug | 3 - High | Error while executing the DBScripts ‘3_KeysAndIndex_SIC' script due to duplicate key found for the object name 'dbo.PickingTripStaging' | Prashant P. Singh | Closed | 2016-04-22 08:20 | Sharada Raghunatha
13931 | Bug | 3 - High | Error while executing the DBScripts ‘2_TablesAndTypes_SIC’. | Prashant P. Singh | Closed | 2016-04-22 05:01 | Sharada Raghunatha
13905 | Bug | 3 - High | Pickingtrips not created due to version mismatch of Interfaces dll when XY is switched ON | Madhuri SriLalitha | Closed | 2016-04-20 08:25 | Sharada Raghunatha
13903 | Bug | 3 - High | Trays not getting sync with Pickingservice dB due to duplicate TPNB in Plutitems table | Likith Vishwanath | Closed | 2016-04-20 07:22 | Sharada Raghunatha
13902 | Bug | 3 - High | Status update to 2 in Request table of dxsh, before trays getting sync with Pickingservice DB | Madhuri SriLalitha | Closed | 2016-04-20 06:31 | Sharada Raghunatha
13901 | Bug | 3 - High | DCOS test box trays not getting sync with pickingservice DB due to Invalid Operation Exception : null value cannot be assigned to a member with type System.Int32 which is a non-nullable value type exception. | Neema Srivastava | Ready for Test | 2016-04-20 05:57 | Sharada Raghunatha
13873 | Bug | 5 - Low | Whenever Scheduling is clicked , getting Mock factory error in PickingComponent logs. | Madhuri SriLalitha | Closed | 2016-04-18 10:46 | Sharada Raghunatha
13872 | Bug | 3 - High | While we trigger scheduling, Picking Component is not being invoked for each trigger. | Madhuri SriLalitha | Closed | 2016-04-18 10:25 | Sharada Raghunatha
13871 | Bug | 3 - High | Trays are not getting syn with Picking service due to invalid column names IsPLUSubs and WeightedRecommendedSubs | Neema Srivastava | Closed | 2016-04-18 10:20 | Sharada Raghunatha
13870 | Bug | 3 - High | In DCOS test box, trays created in dxsh are not getting synchronized with Pickingservice db due to Invalid column name 'IsEnabled'. | Neema Srivastava | Ready for Test | 2016-04-18 10:05 | Sharada Raghunatha
13869 | Bug | 3 - High | All trays created in dxsh are not getting synchronized with Pickingservice dB, we could see mismatch in the number of trays synchronised due to deadlock issue. | Quader Khan (DOTCOM\zd46) | Closed | 2016-04-18 09:58 | Sharada Raghunatha
13867 | Bug | 3 - High | All trays created in dxsh are not getting synchronized with Pickingservice dB, we could see mismatch in the number of trays synchronised due to deadlock issue. | Quader Khan (DOTCOM\zd46) | Ignored | 2016-04-18 08:41 | Sharada Raghunatha
13865 | Bug | 3 - High | DCOS test box trays not getting sync with pickingservice DB due to Invalid Operation Exception : null value cannot be assigned to a member with type System.Int32 which is a non-nullable value type exception. | Sharada Raghunatha | Deleted | 2016-04-18 08:28 | Sharada Raghunatha
13861 | Bug | 3 - High | Once the thershold met Request ID is failing to sent to Picking DB to generate the pick trips when SIC is turn ON. | Vinod Yadawad | Closed | 2016-04-15 09:59 | Renuka Vutukuri
13677 | Bug | 3 - High | Pickingtrips are not processing and coming up with error Ambiguous column name ‘PickingTripID’ | Shailendra Tripathi | Ready for Test | 2016-04-06 13:07 | Sharada Raghunatha
13665 | Bug | 4 - Medium | Scheduling is failing when SIC ON due to permission issue | Narayana Shanubhogh | Closed | 2016-04-05 10:49 | Sharada Raghunatha
13664 | Bug | 3 - High | Unable to do SOD due to System.IO.FileLoadException | Madhuri SriLalitha | Closed | 2016-04-05 10:15 | Sharada Raghunatha
13657 | Bug | 3 - High | Scheduling failing due to no data exist in Dispatch area table. | Sharada Raghunatha | Closed | 2016-04-04 11:57 | Sharada Raghunatha
13656 | Bug | 2 - Critical | Scheduling failing due to Unity config version mismatach | Madhuri SriLalitha | Closed | 2016-04-04 11:50 | Sharada Raghunatha
13556 | Bug | 3 - High | Dispatch area and Vehicle type not getting updated when C&C parameter is On and CFL parameter is off | Bharati Kandakumar | Closed | 2016-03-30 06:38 | Bharati Kandakumar
13555 | Bug | 3 - High | Same friendly van trip is assigned for both cfs and cfl unrouted vans though both are of different vehicle trips | Bharati Kandakumar | Closed | 2016-03-30 06:31 | Bharati Kandakumar
13435 | Bug | 3 - High | Trays are created,but trolleys are not assigned.once the threshold met, new trays are not getting created for the same products. | Renuka Vutukuri | Closed | 2016-03-24 05:13 | Renuka Vutukuri
13434 | Bug | 3 - High | Trays are created,trolleys are assigned,but the pick trips are not generated.once the threshold met, duplicate trays are creating for the same product with same quantity. | Renuka Vutukuri | Closed | 2016-03-24 05:11 | Renuka Vutukuri
13432 | Bug | 3 - High | Errors in dms page, once clicked on generate non early pick trays for a specific zone before the threshold met | Renuka Vutukuri | Closed | 2016-03-24 05:08 | Renuka Vutukuri
13431 | Bug | 3 - High | Trays are not getting created for the remaining items once the picker picks the partial items/quantity. | Renuka Vutukuri | Closed | 2016-03-24 05:07 | Renuka Vutukuri
13430 | Bug | 3 - High | Trays are not getting created once the threshold met by POP | Renuka Vutukuri | Closed | 2016-03-24 05:05 | Renuka Vutukuri
13429 | Bug | 2 - Critical | Once the early pick flag is Turned Off trays are not getting created. | Anirban Biswas (DOTCOM\ZL52) | Closed | 2016-03-24 05:02 | Renuka Vutukuri
13377 | Bug | 3 - High | Unrouted CFS and CFL Orders are getting assigned with the Vehicletype and Dispatch Area as NULL | Bharati Kandakumar | Closed | 2016-03-18 11:37 | Shree Harsha
13372 | Bug | 3 - High | CFS Vehicletrip is getting assigned to both CFL and CFS Orders, when both kind of orders CFL and CFS are placed together | Bharati Kandakumar | Closed | 2016-03-18 11:28 | Shree Harsha

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | 2016-05-12 08:02 | value doesn't matter | [Backlog]\Contributors | Deleted | 1 - Blocking | [Backlog]\Contributors | Active | Deferred | Abdul Rakheeb Khayum | Blocked | Ajay Parmar | Broken | Complete | [Backlog]\Contributors | Active | Aborted | [Backlog]\Contributors | Deleted | [Backlog]\Contributors | Active | Aborted | Abdul Rakheeb Khayum | Closed | Acceptance Test | [Backlog]\Contributors | Deleted | 1 - Blocking | \ | \ | 1 - Blocking | [Backlog]\Contributors | Active
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd/MM/yyyy HH:mm | readOnlyTestRange_General | [Backlog]\Project Administrators | Failed | 2 - Critical | [Backlog]\Project Administrators | Closed | Descoped | Abhay Prasad | Deleted | Amit Rohatgi | Deleted | Deleted | [Backlog]\Project Administrators | Closed | Deleted | [Backlog]\Project Administrators | Descoped | [Backlog]\Project Administrators | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Sprint Retrospective_System.State | Deleted | Abhay Prasad | Open | Bug | [Backlog]\Project Administrators | Failed | 2 - Critical | \Automation | \Automation | 2 - Critical | [Backlog]\Project Administrators | Closed
|  |  |  | Abdul Rakheeb Khayum | Not Implemented | 3 - High | Abdul Rakheeb Khayum | Deleted | Done | Abhilash Raghavendra | Not Blocking | Aniruddh Joshi | Deprecated | In Progress | Abdul Rakheeb Khayum | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Shared Steps_System.State | Done | Abdul Rakheeb Khayum | Done | Abdul Rakheeb Khayum |  | Done | Abhilash Raghavendra | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Wastage_System.State | Epic | Abdul Rakheeb Khayum | Not Implemented | 3 - High | \Checkout | \Automation\Sprint 1 | 3 - High | Abdul Rakheeb Khayum | Deleted
|  |  |  | Abhay Prasad | Passed | 4 - Medium | Abhay Prasad | Ignored | Duplicate | Ajay Budhiworthy | Open | Joby Thomas | Descoped | OnHold | Abhay Prasad |  | In Progress | Abhay Prasad | In Progress | Abhay Prasad |  | In Progress | Ajay Budhiworthy |  | Impediment | Abhay Prasad | Passed | 4 - Medium | \Checkout\Checkout Exceptions | \Automation\Sprint 1\ICP | 4 - Medium | Abhay Prasad | Ignored
|  |  |  | Abhilash Raghavendra | Ready for Test | 5 - Low | Abhilash Raghavendra | Ready for Test | In Progress | Ajay Parmar | Resolved | Mahaboob Peer | Done | Viable | Abhilash Raghavendra |  | Not Started | Abhilash Raghavendra | Not Started | Abhilash Raghavendra |  | Not Started | Ajay Parmar |  | Product Backlog Item | Abhilash Raghavendra | Ready for Test | 5 - Low | \Checkout\Checkout Exceptions\Card Exceptions | \Automation\Sprint 2 | 5 - Low | Abhilash Raghavendra | Ready for Test
|  |  |  | Ajay Budhiworthy | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Acceptance Test_System.State | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Bug_Scrum.v3.TestingImpact | Ajay Budhiworthy | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Bug_System.State | Not Ready | Ajit Merchere | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Impediment_System.State | Manohar Kotagi | In Progress | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Release_System.State | Ajay Budhiworthy |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Sprint_System.State | Ajay Budhiworthy | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Sprint Backlog Task_System.State | Ajay Budhiworthy |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Team Sprint_System.State | Ajit Merchere |  | Release | Ajay Budhiworthy | Active | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Scrum.v3.TestingImpact | \Checkout\Checkout Exceptions\Product Exceptions | \Automation\Sprint 2\ICP | VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_8C-93-5A-D6-44-AC-7E-82-7C-D6-A6-5C-E9-D6-3C-73-82-39-6E-A9 | Ajay Budhiworthy | VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_D4-7D-40-1C-96-29-9D-72-B7-1F-2D-14-55-78-A9-90-F2-E2-3E-73
|  |  |  | Ajay Parmar |  |  | Ajay Parmar |  | Rejected | Akshata Rane |  | Nabagat Purohit | Not Started |  | Ajay Parmar |  |  | Ajay Parmar |  | Ajay Parmar |  |  | Akshata Rane |  | Shared Steps | Ajay Parmar | Closed |  | \Checkout\DMS Checkout Summary Page | \Automation\Sprint 3 |  | Ajay Parmar
|  |  |  | Ajit Merchere |  |  | Ajit Merchere |  | Sprint Ready | Amit A. Kumar |  | Prashanth Lakshman Rao | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Product Backlog Item_System.State |  | Ajit Merchere |  |  | Ajit Merchere |  | Ajit Merchere |  |  | Amit A. Kumar |  | Sprint | Ajit Merchere | Ignored |  | \Checkout\Order Checkout | \Automation\Sprint 3\ICP |  | Ajit Merchere
|  |  |  | Akshata Rane |  |  | Akshata Rane |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Epic_System.State | Amrutha Vas |  | preeti chander |  |  | Akshata Rane |  |  | Akshata Rane |  | Akshata Rane |  |  | Amrutha Vas |  | Sprint Backlog Task | Akshata Rane | Deferred |  | \Checkout\Order ReCheckout | \Catch Weight |  | Akshata Rane
|  |  |  | Amit A. Kumar |  |  | Amit A. Kumar |  |  | Anirban Biswas (DOTCOM\ZL52) |  | Raghavendra Rao |  |  | Amit A. Kumar |  |  | Amit A. Kumar |  | Amit A. Kumar |  |  | Anirban Biswas (DOTCOM\ZL52) |  | Sprint Retrospective | Amit A. Kumar | Descoped |  | \Checkout\Order Refund | \Catch Weight\Hardening |  | Amit A. Kumar
|  |  |  | Amrutha Vas |  |  | Amrutha Vas |  |  | Ankith Pareek |  | Rajesh G. Jingade |  |  | Amrutha Vas |  |  | Amrutha Vas |  | Amrutha Vas |  |  | Ankith Pareek |  | Team Sprint | Amrutha Vas | Done |  | \Checkout\Order Refund\Partial Refund | \Catch Weight\Hardening\Quasar |  | Amrutha Vas
|  |  |  | Anirban Biswas (DOTCOM\ZL52) |  |  | Anirban Biswas (DOTCOM\ZL52) |  |  | Anudeep Kamisetty |  | Rajkumar Pahari |  |  | Anirban Biswas (DOTCOM\ZL52) |  |  | Anirban Biswas (DOTCOM\ZL52) |  | Anirban Biswas (DOTCOM\ZL52) |  |  | Anudeep Kamisetty |  | Wastage | Anirban Biswas (DOTCOM\ZL52) | Duplicate |  | \Checkout\Order Refund\Whole Order Refund | \Catch Weight\Sprint 1 |  | Anirban Biswas (DOTCOM\ZL52)
|  |  |  | Ankith Pareek |  |  | Ankith Pareek |  |  | Apparao Kandipilli |  | Ranjith Sundarrajan |  |  | Ankith Pareek |  |  | Ankith Pareek |  | Ankith Pareek |  |  | Apparao Kandipilli |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_System.WorkItemType | Ankith Pareek | In Progress |  | \Checkout\Order Refund\Whole Order Refund\With Out Service Charge | \Catch Weight\Sprint 1\Pinnacle |  | Ankith Pareek
|  |  |  | Anudeep Kamisetty |  |  | Anudeep Kamisetty |  |  | Arpita Mathur |  | Robin Mathew Thomas |  |  | Anudeep Kamisetty |  |  | Anudeep Kamisetty |  | Anudeep Kamisetty |  |  | Arpita Mathur |  |  | Anudeep Kamisetty | Not Ready |  | \Checkout\Order Refund\Whole Order Refund\With Service Charge | \Catch Weight\Sprint 1\Quasar |  | Anudeep Kamisetty
|  |  |  | Apparao Kandipilli |  |  | Apparao Kandipilli |  |  | Arun Narayanaswamy |  | Roshini Issac |  |  | Apparao Kandipilli |  |  | Apparao Kandipilli |  | Apparao Kandipilli |  |  | Arun Narayanaswamy |  |  | Apparao Kandipilli | Rejected |  | \Checkout\Order ReRefund | \Catch Weight\Sprint 2 |  | Apparao Kandipilli
|  |  |  | Arpita Mathur |  |  | Arpita Mathur |  |  | ArunKumar Gopalan |  | Saravanan Susairaj |  |  | Arpita Mathur |  |  | Arpita Mathur |  | Arpita Mathur |  |  | ArunKumar Gopalan |  |  | Arpita Mathur | Sprint Ready |  | \CICD | \Catch Weight\Sprint 2\Mercurians |  | Arpita Mathur
|  |  |  | Arun Narayanaswamy |  |  | Arun Narayanaswamy |  |  | Ashish Mahajan |  | Sarvesh Upadhyay |  |  | Arun Narayanaswamy |  |  | Arun Narayanaswamy |  | Arun Narayanaswamy |  |  | Ashish Mahajan |  |  | Arun Narayanaswamy | Blocked |  | \CICD\Deployment | \Catch Weight\Sprint 2\Pinnacle |  | Arun Narayanaswamy
|  |  |  | ArunKumar Gopalan |  |  | ArunKumar Gopalan |  |  | Ashish x. Gupta |  | Shree Harsha |  |  | ArunKumar Gopalan |  |  | ArunKumar Gopalan |  | ArunKumar Gopalan |  |  | Ashish x. Gupta |  |  | ArunKumar Gopalan | Not Blocking |  | \CICD\Jenkins | \Catch Weight\Sprint 2\Quasar |  | ArunKumar Gopalan
|  |  |  | Ashish Mahajan |  |  | Ashish Mahajan |  |  | ashok balakrishnan |  | Sivakumar Muniswamy |  |  | Ashish Mahajan |  |  | Ashish Mahajan |  | Ashish Mahajan |  |  | ashok balakrishnan |  |  | Ashish Mahajan | Open |  | \CICD\Nexus | \Catch Weight\Sprint 3 |  | Ashish Mahajan
|  |  |  | Ashish x. Gupta |  |  | Ashish x. Gupta |  |  | Avinash Hegdal |  | Srikanth X Seshabhattaru |  |  | Ashish x. Gupta |  |  | Ashish x. Gupta |  | Ashish x. Gupta |  |  | Avinash Hegdal |  |  | Ashish x. Gupta | Resolved |  | \CICD\Nuget | \Catch Weight\Sprint 3\Elites |  | Ashish x. Gupta
|  |  |  | ashok balakrishnan |  |  | ashok balakrishnan |  |  | Balaji S |  | Srinivasa Dasari |  |  | ashok balakrishnan |  |  | ashok balakrishnan |  | ashok balakrishnan |  |  | Balaji S |  |  | ashok balakrishnan | Broken |  | \CICD\Sonar | \Catch Weight\Sprint 3\Mercurians |  | ashok balakrishnan
|  |  |  | Avinash Hegdal |  |  | Avinash Hegdal |  |  | Bharati Kandakumar |  | Sudheer Eedunoori |  |  | Avinash Hegdal |  |  | Avinash Hegdal |  | Avinash Hegdal |  |  | Bharati Kandakumar |  |  | Avinash Hegdal | Deprecated |  | \CICD\Test | \Catch Weight\Sprint 3\Pacers |  | Avinash Hegdal
|  |  |  | Balaji S |  |  | Balaji S |  |  | Bhaskar Jagadeesh |  | Sumit Gupta |  |  | Balaji S |  |  | Balaji S |  | Balaji S |  |  | Bhaskar Jagadeesh |  |  | Balaji S | Not Started |  | \CICD\TFS | \Catch Weight\Sprint 3\Pinnacle |  | Balaji S
|  |  |  | Bharati Kandakumar |  |  | Bharati Kandakumar |  |  | Bhavya Anantharamu |  | Vemana Anne |  |  | Bharati Kandakumar |  |  | Bharati Kandakumar |  | Bharati Kandakumar |  |  | Bhavya Anantharamu |  |  | Bharati Kandakumar | Complete |  | \Delivery | \Catch Weight\Sprint 3\Quasar |  | Bharati Kandakumar
|  |  |  | Bhaskar Jagadeesh |  |  | Bhaskar Jagadeesh |  |  | Bhupender Singh |  | Vishwa venkatareddy |  |  | Bhaskar Jagadeesh |  |  | Bhaskar Jagadeesh |  | Bhaskar Jagadeesh |  |  | Bhupender Singh |  |  | Bhaskar Jagadeesh | OnHold |  | \Delivery\Reach Collect Journey | \CICD |  | Bhaskar Jagadeesh
|  |  |  | Bhavya Anantharamu |  |  | Bhavya Anantharamu |  |  | Danish Garg |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Product Backlog Item_System.AssignedTo |  |  | Bhavya Anantharamu |  |  | Bhavya Anantharamu |  | Bhavya Anantharamu |  |  | Danish Garg |  |  | Bhavya Anantharamu | Viable |  | \Delivery\Reach Items Returned | \CICD\Sprint 1 |  | Bhavya Anantharamu
|  |  |  | Bhupender Singh |  |  | Bhupender Singh |  |  | deepak rao |  |  |  |  | Bhupender Singh |  |  | Bhupender Singh |  | Bhupender Singh |  |  | deepak rao |  |  | Bhupender Singh | Aborted |  | \Delivery\Reach Return Journey | \CICD\Sprint 2 |  | Bhupender Singh
|  |  |  | Danish Garg |  |  | Danish Garg |  |  | Diana Matei |  |  |  |  | Danish Garg |  |  | Danish Garg |  | Danish Garg |  |  | Diana Matei |  |  | Danish Garg | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_System.State |  | \Delivery\Reach Software Update | \CICD\Sprint 3 |  | Danish Garg
|  |  |  | deepak rao |  |  | deepak rao |  |  | Dipak Mistry |  |  |  |  | deepak rao |  |  | deepak rao |  | deepak rao |  |  | Dipak Mistry |  |  | deepak rao |  |  | \Documentations | \CICD\Sprint 3\ICP |  | deepak rao
|  |  |  | Diana Matei |  |  | Diana Matei |  |  | Divya Ramachandra |  |  |  |  | Diana Matei |  |  | Diana Matei |  | Diana Matei |  |  | Divya Ramachandra |  |  | Diana Matei |  |  | \Documentations\Customer Delivery Note | \CICD\Sprint 4 |  | Diana Matei
|  |  |  | Dipak Mistry |  |  | Dipak Mistry |  |  | Fayaz Ahamed |  |  |  |  | Dipak Mistry |  |  | Dipak Mistry |  | Dipak Mistry |  |  | Fayaz Ahamed |  |  | Dipak Mistry |  |  | \Documentations\Delivery Manifest | \CICD\Sprint 4\ICP |  | Dipak Mistry
|  |  |  | Divya Ramachandra |  |  | Divya Ramachandra |  |  | Gopikrishna Gopal |  |  |  |  | Divya Ramachandra |  |  | Divya Ramachandra |  | Divya Ramachandra |  |  | Gopikrishna Gopal |  |  | Divya Ramachandra |  |  | \Documentations\Refund Reciept | \CICD\Sprint 5 |  | Divya Ramachandra
|  |  |  | Fayaz Ahamed |  |  | Fayaz Ahamed |  |  | Hannah Thomas |  |  |  |  | Fayaz Ahamed |  |  | Fayaz Ahamed |  | Fayaz Ahamed |  |  | Hannah Thomas |  |  | Fayaz Ahamed |  |  | \Documentations\Van Loading Sheet | \CICD\Sprint 5\ICP |  | Fayaz Ahamed
|  |  |  | Gopikrishna Gopal |  |  | Gopikrishna Gopal |  |  | Hare K. Parida |  |  |  |  | Gopikrishna Gopal |  |  | Gopikrishna Gopal |  | Gopikrishna Gopal |  |  | Hare K. Parida |  |  | Gopikrishna Gopal |  |  | \Documentations\Wine Reciept | \CICD\Sprint 6 |  | Gopikrishna Gopal
|  |  |  | Hannah Thomas |  |  | Hannah Thomas |  |  | Harish Sukumar |  |  |  |  | Hannah Thomas |  |  | Hannah Thomas |  | Hannah Thomas |  |  | Harish Sukumar |  |  | Hannah Thomas |  |  | \Dotcom Management System | \CICD\Sprint 6\ICP |  | Hannah Thomas
|  |  |  | Hare K. Parida |  |  | Hare K. Parida |  |  | Harsha Amanaganti |  |  |  |  | Hare K. Parida |  |  | Hare K. Parida |  | Hare K. Parida |  |  | Harsha Amanaganti |  |  | Hare K. Parida |  |  | \Dotcom Management System\Driver Management | \CICD\Sprint 7 |  | Hare K. Parida
|  |  |  | Harish Sukumar |  |  | Harish Sukumar |  |  | Hemanth Shetty |  |  |  |  | Harish Sukumar |  |  | Harish Sukumar |  | Harish Sukumar |  |  | Hemanth Shetty |  |  | Harish Sukumar |  |  | \Dotcom Management System\Driver Management\Assign CDAs | \CICD\Sprint 7\ICP |  | Harish Sukumar
|  |  |  | Harsha Amanaganti |  |  | Harsha Amanaganti |  |  | Humaira Tazyeen |  |  |  |  | Harsha Amanaganti |  |  | Harsha Amanaganti |  | Harsha Amanaganti |  |  | Humaira Tazyeen |  |  | Harsha Amanaganti |  |  | \Dotcom Management System\Driver Management\CDA DownTime | \COI |  | Harsha Amanaganti
|  |  |  | Hemanth Shetty |  |  | Hemanth Shetty |  |  | Indira K P |  |  |  |  | Hemanth Shetty |  |  | Hemanth Shetty |  | Hemanth Shetty |  |  | Indira K P |  |  | Hemanth Shetty |  |  | \Dotcom Management System\Driver Management\CDA Post Code Setup | \COI\Hardening |  | Hemanth Shetty
|  |  |  | Humaira Tazyeen |  |  | Humaira Tazyeen |  |  | Jayaraj Achikanath Chirakkar |  |  |  |  | Humaira Tazyeen |  |  | Humaira Tazyeen |  | Humaira Tazyeen |  |  | Jayaraj Achikanath Chirakkar |  |  | Humaira Tazyeen |  |  | \Dotcom Management System\Driver Management\CDA Team List | \COI\Hardening\Punters |  | Humaira Tazyeen
|  |  |  | Indira K P |  |  | Indira K P |  |  | Joby Thomas |  |  |  |  | Indira K P |  |  | Indira K P |  | Indira K P |  |  | Joby Thomas |  |  | Indira K P |  |  | \Dotcom Management System\Driver Management\CDA Team Setup | \COI\Hardening\Quasar |  | Indira K P
|  |  |  | Jayaraj Achikanath Chirakkar |  |  | Jayaraj Achikanath Chirakkar |  |  | Kamal KishoreAgarwal |  |  |  |  | Jayaraj Achikanath Chirakkar |  |  | Jayaraj Achikanath Chirakkar |  | Jayaraj Achikanath Chirakkar |  |  | Kamal KishoreAgarwal |  |  | Jayaraj Achikanath Chirakkar |  |  | \Dotcom Management System\Driver Management\CDA Trip Allocations | \COI\Sprint 0 |  | Jayaraj Achikanath Chirakkar
|  |  |  | Joby Thomas |  |  | Joby Thomas |  |  | Kamalakshi M |  |  |  |  | Joby Thomas |  |  | Joby Thomas |  | Joby Thomas |  |  | Kamalakshi M |  |  | Joby Thomas |  |  | \Dotcom Management System\Driver Management\Delivery Instructions | \COI\Sprint 0\Elites |  | Joby Thomas
|  |  |  | Kamal KishoreAgarwal |  |  | Kamal KishoreAgarwal |  |  | Karthik Rao |  |  |  |  | Kamal KishoreAgarwal |  |  | Kamal KishoreAgarwal |  | Kamal KishoreAgarwal |  |  | Karthik Rao |  |  | Kamal KishoreAgarwal |  |  | \Dotcom Management System\Driver Management\Out of Slot Orders | \COI\Sprint 1 |  | Kamal KishoreAgarwal
|  |  |  | Kamalakshi M |  |  | Kamalakshi M |  |  | KrushnaChandra Sabat |  |  |  |  | Kamalakshi M |  |  | Kamalakshi M |  | Kamalakshi M |  |  | KrushnaChandra Sabat |  |  | Kamalakshi M |  |  | \Dotcom Management System\Driver Management\Reach Message | \COI\Sprint 1\Elites |  | Kamalakshi M
|  |  |  | Karthik Rao |  |  | Karthik Rao |  |  | Lalit Jethani |  |  |  |  | Karthik Rao |  |  | Karthik Rao |  | Karthik Rao |  |  | Lalit Jethani |  |  | Karthik Rao |  |  | \Dotcom Management System\Driver Management\Unallocated CDAs | \COI\Sprint 2 |  | Karthik Rao
|  |  |  | KrushnaChandra Sabat |  |  | KrushnaChandra Sabat |  |  | Lalit Vijay |  |  |  |  | KrushnaChandra Sabat |  |  | KrushnaChandra Sabat |  | KrushnaChandra Sabat |  |  | Lalit Vijay |  |  | KrushnaChandra Sabat |  |  | \Dotcom Management System\Picking Exception Screen | \COI\Sprint 2\Elites |  | KrushnaChandra Sabat
|  |  |  | Lalit Jethani |  |  | Lalit Jethani |  |  | Likith Vishwanath |  |  |  |  | Lalit Jethani |  |  | Lalit Jethani |  | Lalit Jethani |  |  | Likith Vishwanath |  |  | Lalit Jethani |  |  | \Dotcom Management System\Search Pages | \COI\Sprint 2\Punters |  | Lalit Jethani
|  |  |  | Lalit Vijay |  |  | Lalit Vijay |  |  | Madhu Bhat |  |  |  |  | Lalit Vijay |  |  | Lalit Vijay |  | Lalit Vijay |  |  | Madhu Bhat |  |  | Lalit Vijay |  |  | \Dotcom Management System\Search Pages\Order Search | \COI\Sprint 3 |  | Lalit Vijay
|  |  |  | Likith Vishwanath |  |  | Likith Vishwanath |  |  | Madhukar X Kesa |  |  |  |  | Likith Vishwanath |  |  | Likith Vishwanath |  | Likith Vishwanath |  |  | Madhukar X Kesa |  |  | Likith Vishwanath |  |  | \Dotcom Management System\Search Pages\Picktrip Search | \COI\Sprint 3\Avatar |  | Likith Vishwanath
|  |  |  | Madhu Bhat |  |  | Madhu Bhat |  |  | Madhumathi Raman |  |  |  |  | Madhu Bhat |  |  | Madhu Bhat |  | Madhu Bhat |  |  | Madhumathi Raman |  |  | Madhu Bhat |  |  | \Dotcom Management System\Search Pages\Vantrip Search | \COI\Sprint 3\Elites |  | Madhu Bhat
|  |  |  | Madhukar X Kesa |  |  | Madhukar X Kesa |  |  | Madhuri SriLalitha |  |  |  |  | Madhukar X Kesa |  |  | Madhukar X Kesa |  | Madhukar X Kesa |  |  | Madhuri SriLalitha |  |  | Madhukar X Kesa |  |  | \Dotcom Management System\Support Pages | \COI\Sprint 3\Punters |  | Madhukar X Kesa
|  |  |  | Madhumathi Raman |  |  | Madhumathi Raman |  |  | mageshwaran sivaraj |  |  |  |  | Madhumathi Raman |  |  | Madhumathi Raman |  | Madhumathi Raman |  |  | mageshwaran sivaraj |  |  | Madhumathi Raman |  |  | \Dotcom Management System\Team Managemet | \COI\Sprint 4 |  | Madhumathi Raman
|  |  |  | Madhuri SriLalitha |  |  | Madhuri SriLalitha |  |  | Mahaboob Peer |  |  |  |  | Madhuri SriLalitha |  |  | Madhuri SriLalitha |  | Madhuri SriLalitha |  |  | Mahaboob Peer |  |  | Madhuri SriLalitha |  |  | \Dotcom Management System\Team Managemet\Change Password | \COI\Sprint 4\Elites |  | Madhuri SriLalitha
|  |  |  | mageshwaran sivaraj |  |  | mageshwaran sivaraj |  |  | Maibub Patil |  |  |  |  | mageshwaran sivaraj |  |  | mageshwaran sivaraj |  | mageshwaran sivaraj |  |  | Maibub Patil |  |  | mageshwaran sivaraj |  |  | \Dotcom Management System\Team Managemet\Picking Team Leader Setup | \COI\Sprint 4\Punters |  | mageshwaran sivaraj
|  |  |  | Mahaboob Peer |  |  | Mahaboob Peer |  |  | Manish Agrawal |  |  |  |  | Mahaboob Peer |  |  | Mahaboob Peer |  | Mahaboob Peer |  |  | Manish Agrawal |  |  | Mahaboob Peer |  |  | \Dotcom Management System\Team Managemet\Picking Team Lists | \COI\Sprint 5 |  | Mahaboob Peer
|  |  |  | Maibub Patil |  |  | Maibub Patil |  |  | Manish Tripathi |  |  |  |  | Maibub Patil |  |  | Maibub Patil |  | Maibub Patil |  |  | Manish Tripathi |  |  | Maibub Patil |  |  | \Dotcom Management System\Team Managemet\Reset Password | \COI\Sprint 5\Avatar |  | Maibub Patil
|  |  |  | Manish Agrawal |  |  | Manish Agrawal |  |  | Manu Sharma |  |  |  |  | Manish Agrawal |  |  | Manish Agrawal |  | Manish Agrawal |  |  | Manu Sharma |  |  | Manish Agrawal |  |  | \Integration | \COI\Sprint 5\Elites |  | Manish Agrawal
|  |  |  | Manish Tripathi |  |  | Manish Tripathi |  |  | Meghana Singh |  |  |  |  | Manish Tripathi |  |  | Manish Tripathi |  | Manish Tripathi |  |  | Meghana Singh |  |  | Manish Tripathi |  |  | \Integration\EPOD | \COI\Sprint 5\Mercurians |  | Manish Tripathi
|  |  |  | Manu Sharma |  |  | Manu Sharma |  |  | Mohit Sharma |  |  |  |  | Manu Sharma |  |  | Manu Sharma |  | Manu Sharma |  |  | Mohit Sharma |  |  | Manu Sharma |  |  | \Integration\Stock Service | \COI\Sprint 5\Punters |  | Manu Sharma
|  |  |  | Meghana Singh |  |  | Meghana Singh |  |  | Muralidhar Krishnamurthy |  |  |  |  | Meghana Singh |  |  | Meghana Singh |  | Meghana Singh |  |  | Muralidhar Krishnamurthy |  |  | Meghana Singh |  |  | \International | \COI\Sprint 5\Quasars |  | Meghana Singh
|  |  |  | Mohit Sharma |  |  | Mohit Sharma |  |  | Murugeswari Tharmaraj |  |  |  |  | Mohit Sharma |  |  | Mohit Sharma |  | Mohit Sharma |  |  | Murugeswari Tharmaraj |  |  | Mohit Sharma |  |  | \Operational Reports | \Componentization |  | Mohit Sharma
|  |  |  | Muralidhar Krishnamurthy |  |  | Muralidhar Krishnamurthy |  |  | Nabagat Purohit |  |  |  |  | Muralidhar Krishnamurthy |  |  | Muralidhar Krishnamurthy |  | Muralidhar Krishnamurthy |  |  | Nabagat Purohit |  |  | Muralidhar Krishnamurthy |  |  | \Operational Reports\Availability | \Componentization\Sprint 0 |  | Muralidhar Krishnamurthy
|  |  |  | Murugeswari Tharmaraj |  |  | Murugeswari Tharmaraj |  |  | Narayana Shanubhogh |  |  |  |  | Murugeswari Tharmaraj |  |  | Murugeswari Tharmaraj |  | Murugeswari Tharmaraj |  |  | Narayana Shanubhogh |  |  | Murugeswari Tharmaraj |  |  | \Operational Reports\Availability\Daily off sale | \Componentization\Sprint 1 |  | Murugeswari Tharmaraj
|  |  |  | Nabagat Purohit |  |  | Nabagat Purohit |  |  | Neema Srivastava |  |  |  |  | Nabagat Purohit |  |  | Nabagat Purohit |  | Nabagat Purohit |  |  | Neema Srivastava |  |  | Nabagat Purohit |  |  | \Operational Reports\Availability\Departmental Availability | \Componentization\Sprint 1\Rainbow |  | Nabagat Purohit
|  |  |  | Narayana Shanubhogh |  |  | Narayana Shanubhogh |  |  | Niharika Agarwal |  |  |  |  | Narayana Shanubhogh |  |  | Narayana Shanubhogh |  | Narayana Shanubhogh |  |  | Niharika Agarwal |  |  | Narayana Shanubhogh |  |  | \Operational Reports\Availability\Top 50 Products Offsale Today | \Componentization\Sprint 10 |  | Narayana Shanubhogh
|  |  |  | Neema Srivastava |  |  | Neema Srivastava |  |  | Nivedita DasSharma |  |  |  |  | Neema Srivastava |  |  | Neema Srivastava |  | Neema Srivastava |  |  | Nivedita DasSharma |  |  | Neema Srivastava |  |  | \Operational Reports\Delivery | \Componentization\Sprint 10\Quasar |  | Neema Srivastava
|  |  |  | Niharika Agarwal |  |  | Niharika Agarwal |  |  | Palanisamy Jagadeesan |  |  |  |  | Niharika Agarwal |  |  | Niharika Agarwal |  | Niharika Agarwal |  |  | Palanisamy Jagadeesan |  |  | Niharika Agarwal |  |  | \Operational Reports\Delivery\Cda Performance | \Componentization\Sprint 2 |  | Niharika Agarwal
|  |  |  | Nivedita DasSharma |  |  | Nivedita DasSharma |  |  | Pankaj Tiwary |  |  |  |  | Nivedita DasSharma |  |  | Nivedita DasSharma |  | Nivedita DasSharma |  |  | Pankaj Tiwary |  |  | Nivedita DasSharma |  |  | \Operational Reports\Delivery\Loader Management | \Componentization\Sprint 2\Rainbow |  | Nivedita DasSharma
|  |  |  | Palanisamy Jagadeesan |  |  | Palanisamy Jagadeesan |  |  | Prabhakaran Dhandapani |  |  |  |  | Palanisamy Jagadeesan |  |  | Palanisamy Jagadeesan |  | Palanisamy Jagadeesan |  |  | Prabhakaran Dhandapani |  |  | Palanisamy Jagadeesan |  |  | \Operational Reports\Delivery\Reach Signature | \Componentization\Sprint 3 |  | Palanisamy Jagadeesan
|  |  |  | Pankaj Tiwary |  |  | Pankaj Tiwary |  |  | Prabhu Somasundaram |  |  |  |  | Pankaj Tiwary |  |  | Pankaj Tiwary |  | Pankaj Tiwary |  |  | Prabhu Somasundaram |  |  | Pankaj Tiwary |  |  | \Operational Reports\Delivery\Reach Usage | \Componentization\Sprint 3\Rainbow |  | Pankaj Tiwary
|  |  |  | Prabhakaran Dhandapani |  |  | Prabhakaran Dhandapani |  |  | Pradeep Kumar |  |  |  |  | Prabhakaran Dhandapani |  |  | Prabhakaran Dhandapani |  | Prabhakaran Dhandapani |  |  | Pradeep Kumar |  |  | Prabhakaran Dhandapani |  |  | \Operational Reports\Delivery\Team Cda Performance | \Componentization\Sprint 4 |  | Prabhakaran Dhandapani
|  |  |  | Prabhu Somasundaram |  |  | Prabhu Somasundaram |  |  | Pradeep Rao |  |  |  |  | Prabhu Somasundaram |  |  | Prabhu Somasundaram |  | Prabhu Somasundaram |  |  | Pradeep Rao |  |  | Prabhu Somasundaram |  |  | \Operational Reports\Delivery\Van Control Sheet | \Componentization\Sprint 4\Punters |  | Prabhu Somasundaram
|  |  |  | Pradeep Kumar |  |  | Pradeep Kumar |  |  | Prakash KrishnaReddy |  |  |  |  | Pradeep Kumar |  |  | Pradeep Kumar |  | Pradeep Kumar |  |  | Prakash KrishnaReddy |  |  | Pradeep Kumar |  |  | \Operational Reports\Order | \Componentization\Sprint 5 |  | Pradeep Kumar
|  |  |  | Pradeep Rao |  |  | Pradeep Rao |  |  | Prasantha Thondepu |  |  |  |  | Pradeep Rao |  |  | Pradeep Rao |  | Pradeep Rao |  |  | Prasantha Thondepu |  |  | Pradeep Rao |  |  | \Operational Reports\Order\Daily Complaints Non Refund | \Componentization\Sprint 5\Punters |  | Pradeep Rao
|  |  |  | Prakash KrishnaReddy |  |  | Prakash KrishnaReddy |  |  | Prashant P. Singh |  |  |  |  | Prakash KrishnaReddy |  |  | Prakash KrishnaReddy |  | Prakash KrishnaReddy |  |  | Prashant P. Singh |  |  | Prakash KrishnaReddy |  |  | \Operational Reports\Order\Daily Complaints Refund | \Componentization\Sprint 6 |  | Prakash KrishnaReddy
|  |  |  | Prasantha Thondepu |  |  | Prasantha Thondepu |  |  | Prashanth Lakshman Rao |  |  |  |  | Prasantha Thondepu |  |  | Prasantha Thondepu |  | Prasantha Thondepu |  |  | Prashanth Lakshman Rao |  |  | Prasantha Thondepu |  |  | \Operational Reports\Order\Daily Complaints Summary | \Componentization\Sprint 6\Punters |  | Prasantha Thondepu
|  |  |  | Prashant P. Singh |  |  | Prashant P. Singh |  |  | Praveen Shankar |  |  |  |  | Prashant P. Singh |  |  | Prashant P. Singh |  | Prashant P. Singh |  |  | Praveen Shankar |  |  | Prashant P. Singh |  |  | \Operational Reports\Order\Expired Orders | \Componentization\Sprint 7 |  | Prashant P. Singh
|  |  |  | Prashanth Lakshman Rao |  |  | Prashanth Lakshman Rao |  |  | Pravesh Sharma |  |  |  |  | Prashanth Lakshman Rao |  |  | Prashanth Lakshman Rao |  | Prashanth Lakshman Rao |  |  | Pravesh Sharma |  |  | Prashanth Lakshman Rao |  |  | \Operational Reports\Order\Order Details | \Componentization\Sprint 7\Quasar |  | Prashanth Lakshman Rao
|  |  |  | Praveen Shankar |  |  | Praveen Shankar |  |  | preeti chander |  |  |  |  | Praveen Shankar |  |  | Praveen Shankar |  | Praveen Shankar |  |  | preeti chander |  |  | Praveen Shankar |  |  | \Operational Reports\Order\Till Void Tansactions | \Componentization\Sprint 8 |  | Praveen Shankar
|  |  |  | Pravesh Sharma |  |  | Pravesh Sharma |  |  | Priyanku Konar |  |  |  |  | Pravesh Sharma |  |  | Pravesh Sharma |  | Pravesh Sharma |  |  | Priyanku Konar |  |  | Pravesh Sharma |  |  | \Operational Reports\performance | \Componentization\Sprint 8\Quasar |  | Pravesh Sharma
|  |  |  | preeti chander |  |  | preeti chander |  |  | Quader Khan (DOTCOM\zd46) |  |  |  |  | preeti chander |  |  | preeti chander |  | preeti chander |  |  | Quader Khan (DOTCOM\zd46) |  |  | preeti chander |  |  | \Operational Reports\performance\CDA Performance | \Componentization\Sprint 9 |  | preeti chander
|  |  |  | Priyanku Konar |  |  | Priyanku Konar |  |  | Raghavendra Desai |  |  |  |  | Priyanku Konar |  |  | Priyanku Konar |  | Priyanku Konar |  |  | Raghavendra Desai |  |  | Priyanku Konar |  |  | \Operational Reports\performance\Loader Management | \Componentization\Sprint 9\Quasar |  | Priyanku Konar
|  |  |  | Quader Khan (DOTCOM\zd46) |  |  | Quader Khan (DOTCOM\zd46) |  |  | Raghavendra Rao |  |  |  |  | Quader Khan (DOTCOM\zd46) |  |  | Quader Khan (DOTCOM\zd46) |  | Quader Khan (DOTCOM\zd46) |  |  | Raghavendra Rao |  |  | Quader Khan (DOTCOM\zd46) |  |  | \Operational Reports\performance\Reach Signature | \D7 |  | Quader Khan (DOTCOM\zd46)
|  |  |  | Raghavendra Desai |  |  | Raghavendra Desai |  |  | Rajalingam Rajendran |  |  |  |  | Raghavendra Desai |  |  | Raghavendra Desai |  | Raghavendra Desai |  |  | Rajalingam Rajendran |  |  | Raghavendra Desai |  |  | \Operational Reports\performance\Reach Usage | \D7\AutoDCC |  | Raghavendra Desai
|  |  |  | Raghavendra Rao |  |  | Raghavendra Rao |  |  | Rajanish Bhanded (DOTCOM\zp51) |  |  |  |  | Raghavendra Rao |  |  | Raghavendra Rao |  | Raghavendra Rao |  |  | Rajanish Bhanded (DOTCOM\zp51) |  |  | Raghavendra Rao |  |  | \Operational Reports\performance\Team CDA Performance | \D7\AutoDCC\Hardening |  | Raghavendra Rao
|  |  |  | Rajalingam Rajendran |  |  | Rajalingam Rajendran |  |  | Rajesh G. Jingade |  |  |  |  | Rajalingam Rajendran |  |  | Rajalingam Rajendran |  | Rajalingam Rajendran |  |  | Rajesh G. Jingade |  |  | Rajalingam Rajendran |  |  | \Operational Reports\performance\Van Control Sheet | \D7\AutoDCC\Hardening\Mercurians |  | Rajalingam Rajendran
|  |  |  | Rajanish Bhanded (DOTCOM\zp51) |  |  | Rajanish Bhanded (DOTCOM\zp51) |  |  | Rajkumar Pahari |  |  |  |  | Rajanish Bhanded (DOTCOM\zp51) |  |  | Rajanish Bhanded (DOTCOM\zp51) |  | Rajanish Bhanded (DOTCOM\zp51) |  |  | Rajkumar Pahari |  |  | Rajanish Bhanded (DOTCOM\zp51) |  |  | \Operational Reports\Product | \D7\AutoDCC\OPS-LIVE-Defects |  | Rajanish Bhanded (DOTCOM\zp51)
|  |  |  | Rajesh G. Jingade |  |  | Rajesh G. Jingade |  |  | RamaChandraMurthy Thallada |  |  |  |  | Rajesh G. Jingade |  |  | Rajesh G. Jingade |  | Rajesh G. Jingade |  |  | RamaChandraMurthy Thallada |  |  | Rajesh G. Jingade |  |  | \Operational Reports\Product\Non food parcel report | \D7\AutoDCC\Sprint 0 |  | Rajesh G. Jingade
|  |  |  | Rajkumar Pahari |  |  | Rajkumar Pahari |  |  | Ramya R |  |  |  |  | Rajkumar Pahari |  |  | Rajkumar Pahari |  | Rajkumar Pahari |  |  | Ramya R |  |  | Rajkumar Pahari |  |  | \Operational Reports\Product\Picked and labelled wine report | \D7\AutoDCC\Sprint 0\Mercurians |  | Rajkumar Pahari
|  |  |  | RamaChandraMurthy Thallada |  |  | RamaChandraMurthy Thallada |  |  | Ranjith Sundarrajan |  |  |  |  | RamaChandraMurthy Thallada |  |  | RamaChandraMurthy Thallada |  | RamaChandraMurthy Thallada |  |  | Ranjith Sundarrajan |  |  | RamaChandraMurthy Thallada |  |  | \Operational Reports\Product\Secure product report | \D7\AutoDCC\Sprint 1 |  | RamaChandraMurthy Thallada
|  |  |  | Ramya R |  |  | Ramya R |  |  | Renuka Vutukuri |  |  |  |  | Ramya R |  |  | Ramya R |  | Ramya R |  |  | Renuka Vutukuri |  |  | Ramya R |  |  | \Operational Reports\Product\Wine parcel report | \D7\AutoDCC\Sprint 1\Mercurians |  | Ramya R
|  |  |  | Ranjith Sundarrajan |  |  | Ranjith Sundarrajan |  |  | Robin Mathew Thomas |  |  |  |  | Ranjith Sundarrajan |  |  | Ranjith Sundarrajan |  | Ranjith Sundarrajan |  |  | Robin Mathew Thomas |  |  | Ranjith Sundarrajan |  |  | \Operational Reports\Trends | \D7\AutoDCC\Sprint 2 |  | Ranjith Sundarrajan
|  |  |  | Renuka Vutukuri |  |  | Renuka Vutukuri |  |  | Sachidananda V S |  |  |  |  | Renuka Vutukuri |  |  | Renuka Vutukuri |  | Renuka Vutukuri |  |  | Sachidananda V S |  |  | Renuka Vutukuri |  |  | \Operational Reports\Trends\Availability Trend | \D7\AutoDCC\Sprint 2\Mercurians |  | Renuka Vutukuri
|  |  |  | Robin Mathew Thomas |  |  | Robin Mathew Thomas |  |  | Sairam Sundaram |  |  |  |  | Robin Mathew Thomas |  |  | Robin Mathew Thomas |  | Robin Mathew Thomas |  |  | Sairam Sundaram |  |  | Robin Mathew Thomas |  |  | \Operational Reports\Trends\Complaints Trend | \D7\AutoDCC\Sprint 3 |  | Robin Mathew Thomas
|  |  |  | Sachidananda V S |  |  | Sachidananda V S |  |  | Sajith Balakrishnan |  |  |  |  | Sachidananda V S |  |  | Sachidananda V S |  | Sachidananda V S |  |  | Sajith Balakrishnan |  |  | Sachidananda V S |  |  | \Operational Reports\Trends\Daily Sales and Orders | \D7\AutoDCC\Sprint 3\Mercurians |  | Sachidananda V S
|  |  |  | Sairam Sundaram |  |  | Sairam Sundaram |  |  | Sandeep Kumar |  |  |  |  | Sairam Sundaram |  |  | Sairam Sundaram |  | Sairam Sundaram |  |  | Sandeep Kumar |  |  | Sairam Sundaram |  |  | \Operational Reports\Trends\Weekly Sales and Orders | \D7\AutoDCC\Sprint 4 |  | Sairam Sundaram
|  |  |  | Sajith Balakrishnan |  |  | Sajith Balakrishnan |  |  | Sanjay Kurr |  |  |  |  | Sajith Balakrishnan |  |  | Sajith Balakrishnan |  | Sajith Balakrishnan |  |  | Sanjay Kurr |  |  | Sajith Balakrishnan |  |  | \PCS Admin | \D7\AutoDCC\Sprint 4\Mercurians |  | Sajith Balakrishnan
|  |  |  | Sandeep Kumar |  |  | Sandeep Kumar |  |  | Sarfraz Khan |  |  |  |  | Sandeep Kumar |  |  | Sandeep Kumar |  | Sandeep Kumar |  |  | Sarfraz Khan |  |  | Sandeep Kumar |  |  | \Picking | \D7\AutoDCC\Sprint 5 |  | Sandeep Kumar
|  |  |  | Sanjay Kurr |  |  | Sanjay Kurr |  |  | Saritha Reddy |  |  |  |  | Sanjay Kurr |  |  | Sanjay Kurr |  | Sanjay Kurr |  |  | Saritha Reddy |  |  | Sanjay Kurr |  |  | \Picking\Auto Audit | \D7\AutoDCC\Sprint 5\Mercurians |  | Sanjay Kurr
|  |  |  | Sarfraz Khan |  |  | Sarfraz Khan |  |  | Sarvesh Upadhyay |  |  |  |  | Sarfraz Khan |  |  | Sarfraz Khan |  | Sarfraz Khan |  |  | Sarvesh Upadhyay |  |  | Sarfraz Khan |  |  | \Picking\Auto Substitution | \D7\AutoDCC\Sprint 6 |  | Sarfraz Khan
|  |  |  | Saritha Reddy |  |  | Saritha Reddy |  |  | Seethalakshmi Ponnusamy |  |  |  |  | Saritha Reddy |  |  | Saritha Reddy |  | Saritha Reddy |  |  | Seethalakshmi Ponnusamy |  |  | Saritha Reddy |  |  | \Picking\Collect Picking Trip | \D7\AutoDCC\Sprint 6\Mercurians |  | Saritha Reddy
|  |  |  | Sarvesh Upadhyay |  |  | Sarvesh Upadhyay |  |  | Senthil Sivanath |  |  |  |  | Sarvesh Upadhyay |  |  | Sarvesh Upadhyay |  | Sarvesh Upadhyay |  |  | Senthil Sivanath |  |  | Sarvesh Upadhyay |  |  | \Picking\Counters | \D7\AutoDCC\Sprint 7 |  | Sarvesh Upadhyay
|  |  |  | Seethalakshmi Ponnusamy |  |  | Seethalakshmi Ponnusamy |  |  | Shailendra Tripathi |  |  |  |  | Seethalakshmi Ponnusamy |  |  | Seethalakshmi Ponnusamy |  | Seethalakshmi Ponnusamy |  |  | Shailendra Tripathi |  |  | Seethalakshmi Ponnusamy |  |  | \Picking\Early Picking | \D7\AutoDCC\Sprint 7\Mercurians |  | Seethalakshmi Ponnusamy
|  |  |  | Senthil Sivanath |  |  | Senthil Sivanath |  |  | Sharada Raghunatha |  |  |  |  | Senthil Sivanath |  |  | Senthil Sivanath |  | Senthil Sivanath |  |  | Sharada Raghunatha |  |  | Senthil Sivanath |  |  | \Picking\Manual Audit | \D7\AutoDCC\Sprint 8 |  | Senthil Sivanath
|  |  |  | Shailendra Tripathi |  |  | Shailendra Tripathi |  |  | Shilpa Prabhu |  |  |  |  | Shailendra Tripathi |  |  | Shailendra Tripathi |  | Shailendra Tripathi |  |  | Shilpa Prabhu |  |  | Shailendra Tripathi |  |  | \Picking\Normal Picking | \D7\AutoDCC\Sprint 8\Mercurians |  | Shailendra Tripathi
|  |  |  | Sharada Raghunatha |  |  | Sharada Raghunatha |  |  | shivam sharma |  |  |  |  | Sharada Raghunatha |  |  | Sharada Raghunatha |  | Sharada Raghunatha |  |  | shivam sharma |  |  | Sharada Raghunatha |  |  | \Picking\Parcel Picking | \D7\DCC |  | Sharada Raghunatha
|  |  |  | Shilpa Prabhu |  |  | Shilpa Prabhu |  |  | Shree Harsha |  |  |  |  | Shilpa Prabhu |  |  | Shilpa Prabhu |  | Shilpa Prabhu |  |  | Shree Harsha |  |  | Shilpa Prabhu |  |  | \Picking\Pick Ahead | \D7\DCC\Additional Sprint XY Korea |  | Shilpa Prabhu
|  |  |  | shivam sharma |  |  | shivam sharma |  |  | Shruthi Jagadeesh |  |  |  |  | shivam sharma |  |  | shivam sharma |  | shivam sharma |  |  | Shruthi Jagadeesh |  |  | shivam sharma |  |  | \Picking\PLU | \D7\DCC\Additional Sprint XY Korea\Firebirds |  | shivam sharma
|  |  |  | Shree Harsha |  |  | Shree Harsha |  |  | Shruti Tripathi |  |  |  |  | Shree Harsha |  |  | Shree Harsha |  | Shree Harsha |  |  | Shruti Tripathi |  |  | Shree Harsha |  |  | \Picking\Pre Picking | \D7\DCC\Additional Sprint XY Korea\Punters |  | Shree Harsha
|  |  |  | Shruthi Jagadeesh |  |  | Shruthi Jagadeesh |  |  | Siva Valliappa |  |  |  |  | Shruthi Jagadeesh |  |  | Shruthi Jagadeesh |  | Shruthi Jagadeesh |  |  | Siva Valliappa |  |  | Shruthi Jagadeesh |  |  | \Picking\Recomended Substitution | \D7\DCC\Hardening |  | Shruthi Jagadeesh
|  |  |  | Shruti Tripathi |  |  | Shruti Tripathi |  |  | Sivakumar Muniswamy |  |  |  |  | Shruti Tripathi |  |  | Shruti Tripathi |  | Shruti Tripathi |  |  | Sivakumar Muniswamy |  |  | Shruti Tripathi |  |  | \Picking\Return Picking Trip | \D7\DCC\Hardening\Firebirds |  | Shruti Tripathi
|  |  |  | Siva Valliappa |  |  | Siva Valliappa |  |  | Smitha Naidu |  |  |  |  | Siva Valliappa |  |  | Siva Valliappa |  | Siva Valliappa |  |  | Smitha Naidu |  |  | Siva Valliappa |  |  | \Picking\Review Picking | \D7\DCC\Hardening\Mustang |  | Siva Valliappa
|  |  |  | Sivakumar Muniswamy |  |  | Sivakumar Muniswamy |  |  | Sreenuraj Varma |  |  |  |  | Sivakumar Muniswamy |  |  | Sivakumar Muniswamy |  | Sivakumar Muniswamy |  |  | Sreenuraj Varma |  |  | Sivakumar Muniswamy |  |  | \Picking\Scan Item Scan Tray | \D7\DCC\Hardening\Pacers |  | Sivakumar Muniswamy
|  |  |  | Smitha Naidu |  |  | Smitha Naidu |  |  | Suhas Suresh |  |  |  |  | Smitha Naidu |  |  | Smitha Naidu |  | Smitha Naidu |  |  | Suhas Suresh |  |  | Smitha Naidu |  |  | \Picking\Turkey Picking | \D7\DCC\Hardening\Punters |  | Smitha Naidu
|  |  |  | Sreenuraj Varma |  |  | Sreenuraj Varma |  |  | Sumiran Chaudhary |  |  |  |  | Sreenuraj Varma |  |  | Sreenuraj Varma |  | Sreenuraj Varma |  |  | Sumiran Chaudhary |  |  | Sreenuraj Varma |  |  | \Picking\Unpick Items | \D7\DCC\Hardening\Quasar |  | Sreenuraj Varma
|  |  |  | Suhas Suresh |  |  | Suhas Suresh |  |  | Suresh Kalaga |  |  |  |  | Suhas Suresh |  |  | Suhas Suresh |  | Suhas Suresh |  |  | Suresh Kalaga |  |  | Suhas Suresh |  |  | \Picking\Wine Picking | \D7\DCC\Hardening\Rainbow |  | Suhas Suresh
|  |  |  | Sumiran Chaudhary |  |  | Sumiran Chaudhary |  |  | Surjeet Singh |  |  |  |  | Sumiran Chaudhary |  |  | Sumiran Chaudhary |  | Sumiran Chaudhary |  |  | Surjeet Singh |  |  | Sumiran Chaudhary |  |  | \Scheduling | \D7\DCC\Sprint 0 |  | Sumiran Chaudhary
|  |  |  | Suresh Kalaga |  |  | Suresh Kalaga |  |  | Sushma Srinivasa |  |  |  |  | Suresh Kalaga |  |  | Suresh Kalaga |  | Suresh Kalaga |  |  | Sushma Srinivasa |  |  | Suresh Kalaga |  |  | \Scheduling\Click and Collect | \D7\DCC\Sprint 0\FireBirds |  | Suresh Kalaga
|  |  |  | Surjeet Singh |  |  | Surjeet Singh |  |  | Syed Abdul Rehman |  |  |  |  | Surjeet Singh |  |  | Surjeet Singh |  | Surjeet Singh |  |  | Syed Abdul Rehman |  |  | Surjeet Singh |  |  | \Scheduling\Collect From Location | \D7\DCC\Sprint 0\Iteration 0 |  | Surjeet Singh
|  |  |  | Sushma Srinivasa |  |  | Sushma Srinivasa |  |  | Tania Ghosh |  |  |  |  | Sushma Srinivasa |  |  | Sushma Srinivasa |  | Sushma Srinivasa |  |  | Tania Ghosh |  |  | Sushma Srinivasa |  |  | \Scheduling\Paragon | \D7\DCC\Sprint 0\Mustang |  | Sushma Srinivasa
|  |  |  | Syed Abdul Rehman |  |  | Syed Abdul Rehman |  |  | vaibhav gupta |  |  |  |  | Syed Abdul Rehman |  |  | Syed Abdul Rehman |  | Syed Abdul Rehman |  |  | vaibhav gupta |  |  | Syed Abdul Rehman |  |  | \Scheduling\Pick Ahead | \D7\DCC\Sprint 0\Pacers |  | Syed Abdul Rehman
|  |  |  | Tania Ghosh |  |  | Tania Ghosh |  |  | Varun Anil |  |  |  |  | Tania Ghosh |  |  | Tania Ghosh |  | Tania Ghosh |  |  | Varun Anil |  |  | Tania Ghosh |  |  | \Scheduling\RTVS | \D7\DCC\Sprint 0\Punters |  | Tania Ghosh
|  |  |  | vaibhav gupta |  |  | vaibhav gupta |  |  | Vemana Anne |  |  |  |  | vaibhav gupta |  |  | vaibhav gupta |  | vaibhav gupta |  |  | Vemana Anne |  |  | vaibhav gupta |  |  | \Scheduling\Same Day Collection | \D7\DCC\Sprint 0\Quasar |  | vaibhav gupta
|  |  |  | Varun Anil |  |  | Varun Anil |  |  | Vignesh Ramalingam |  |  |  |  | Varun Anil |  |  | Varun Anil |  | Varun Anil |  |  | Vignesh Ramalingam |  |  | Varun Anil |  |  | \Scheduling\Same Day Delivery | \D7\DCC\Sprint 0\Rainbow |  | Varun Anil
|  |  |  | Vemana Anne |  |  | Vemana Anne |  |  | Vinay Javaregowda |  |  |  |  | Vemana Anne |  |  | Vemana Anne |  | Vemana Anne |  |  | Vinay Javaregowda |  |  | Vemana Anne |  |  | \TechnicalDebt | \D7\DCC\Sprint 1 |  | Vemana Anne
|  |  |  | Vignesh Ramalingam |  |  | Vignesh Ramalingam |  |  | Vinay Srivastava |  |  |  |  | Vignesh Ramalingam |  |  | Vignesh Ramalingam |  | Vignesh Ramalingam |  |  | Vinay Srivastava |  |  | Vignesh Ramalingam |  |  | \TechnicalDebt\Alerting and Monitoring | \D7\DCC\Sprint 1\FireBirds |  | Vignesh Ramalingam
|  |  |  | Vinay Javaregowda |  |  | Vinay Javaregowda |  |  | Vinod Yadawad |  |  |  |  | Vinay Javaregowda |  |  | Vinay Javaregowda |  | Vinay Javaregowda |  |  | Vinod Yadawad |  |  | Vinay Javaregowda |  |  | \TechnicalDebt\Application | \D7\DCC\Sprint 1\Mustang |  | Vinay Javaregowda
|  |  |  | Vinay Srivastava |  |  | Vinay Srivastava |  |  | Vivek Shetty |  |  |  |  | Vinay Srivastava |  |  | Vinay Srivastava |  | Vinay Srivastava |  |  | Vivek Shetty |  |  | Vinay Srivastava |  |  | \TechnicalDebt\Application\NPD | \D7\DCC\Sprint 1\Pacers |  | Vinay Srivastava
|  |  |  | Vinod Yadawad |  |  | Vinod Yadawad |  |  | Yathish Chandra |  |  |  |  | Vinod Yadawad |  |  | Vinod Yadawad |  | Vinod Yadawad |  |  | Yathish Chandra |  |  | Vinod Yadawad |  |  | \TechnicalDebt\CD | \D7\DCC\Sprint 1\Punters |  | Vinod Yadawad
|  |  |  | Vivek Shetty |  |  | Vivek Shetty |  |  | Yogesh Gupta |  |  |  |  | Vivek Shetty |  |  | Vivek Shetty |  | Vivek Shetty |  |  | Yogesh Gupta |  |  | Vivek Shetty |  |  | \TechnicalDebt\CI | \D7\DCC\Sprint 1\Quasar |  | Vivek Shetty
|  |  |  | Yathish Chandra |  |  | Yathish Chandra |  |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Impediment_System.AssignedTo |  |  |  |  | Yathish Chandra |  |  | Yathish Chandra |  | Yathish Chandra |  |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Wastage_System.AssignedTo |  |  | Yathish Chandra |  |  | \TechnicalDebt\Code Quality | \D7\DCC\Sprint 1\RainBow |  | Yathish Chandra
|  |  |  | Yogesh Gupta |  |  | Yogesh Gupta | [7 empty] | Yogesh Gupta |  |  | Yogesh Gupta |  | Yogesh Gupta | [5 empty] | Yogesh Gupta |  |  | \TechnicalDebt\Configuration | \D7\DCC\Sprint 2 |  | Yogesh Gupta
|  |  |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Acceptance Test_System.AssignedTo |  |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Bug_System.AssignedTo | [7 empty] | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Shared Steps_System.AssignedTo |  |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Sprint Backlog Task_System.AssignedTo |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_Sprint Retrospective_System.AssignedTo | [5 empty] | Amit Rohatgi |  |  | \TechnicalDebt\DataBase | \D7\DCC\Sprint 2\Firebirds |  | VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_72-59-DC-2E-48-43-09-91-31-DF-1C-B5-50-22-42-33-68-BA-63-6F
[26 empty] | Aniruddh Joshi |  |  | \TechnicalDebt\Environment Setup | \D7\DCC\Sprint 2\Mustang
[26 empty] | Manohar Kotagi |  |  | \TechnicalDebt\Failsafe and Retry | \D7\DCC\Sprint 2\Pacers
[26 empty] | Roshini Issac |  |  | \TechnicalDebt\Logging | \D7\DCC\Sprint 2\Punters
[26 empty] | Saravanan Susairaj |  |  | \TechnicalDebt\Performance | \D7\DCC\Sprint 2\Quasar
[26 empty] | Srikanth X Seshabhattaru |  |  | \TechnicalDebt\Service | \D7\DCC\Sprint 2\Rainbow
[26 empty] | Srinivasa Dasari |  |  | \TechnicalDebt\Standards and Conventions | \D7\DCC\Sprint 3
[26 empty] | Sudheer Eedunoori |  |  | \Tools | \D7\DCC\Sprint 3\Firebirds
[26 empty] | Sumit Gupta |  |  | \Tools\DB Script Gen Tool | \D7\DCC\Sprint 3\Mustang
[26 empty] | Vishwa venkatareddy |  |  | \Tools\E2E Tool | \D7\DCC\Sprint 3\Pacers
[26 empty] | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_System.AssignedTo |  |  | all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_System.AreaPath | \D7\DCC\Sprint 3\Punters
\D7\DCC\Sprint 3\Quasar
\D7\DCC\Sprint 3\Rainbow
\D7\DCC\Sprint 4
\D7\DCC\Sprint 4\Firebirds
\D7\DCC\Sprint 4\Mustang
\D7\DCC\Sprint 4\Pacers
\D7\DCC\Sprint 4\Punters
\D7\DCC\Sprint 4\Quasar
\D7\DCC\Sprint 4\Rainbow
\D7\DCC\Sprint 5
\D7\DCC\Sprint 5\Firebirds
\D7\DCC\Sprint 5\Mustang
\D7\DCC\Sprint 5\Pacers
\D7\DCC\Sprint 5\Punters
\D7\DCC\Sprint 5\Quasar
\D7\DCC\Sprint 5\Rainbow
\D7\DCC\Sprint 6
\D7\DCC\Sprint 6\Firebirds
\D7\DCC\Sprint 6\Mustang
\D7\DCC\Sprint 6\Pacers
\D7\DCC\Sprint 6\Punters
\D7\DCC\Sprint 6\Quasar
\D7\DCC\Sprint 6\Rainbow
\D7\DCC\Sprint 7
\D7\DCC\Sprint 7\Firebirds
\D7\DCC\Sprint 7\Mustang
\D7\DCC\Sprint 7\Pacers
\D7\DCC\Sprint 7\Punters
\D7\DCC\Sprint 7\Quasar
\D7\DCC\Sprint 7\Rainbow
\D7\DCC\Sprint 8
\D7\DCC\Sprint 8\Firebirds
\D7\DCC\Sprint 8\Mustang
\D7\DCC\Sprint 8\Pacers
\D7\DCC\Sprint 8\Punters
\D7\DCC\Sprint 8\Quasar
\D7\DCC\Sprint 8\Rainbow
\D7\DCC\Sprint 9
\D7\DCC\Sprint 9\Punters
\D7\DCC\Topaz Korea Hardening
\D7\DCC\Topaz Korea Hardening\Firebirds
\D7\DCC\Topaz Korea Hardening\Punters
\D8
\D8\Estate-DCC
\D8\Estate-DCC\Sprint 0
\D8\Estate-DCC\Sprint 0\Pacers
\D8\Estate-DCC\Sprint 1
\D8\Estate-DCC\Sprint 1\Pacers
\D8\Estate-DCC\Sprint 2
\D8\Estate-DCC\Sprint 2\Avatar
\D8\Estate-DCC\Sprint 2\Pacers
\D8\Estate-DCC\Sprint 2\Punters
\D8\Estate-DCC\Sprint 3
\D8\Estate-DCC\Sprint 3\Avatar
\D8\Estate-DCC\Sprint 3\Pacers
\D8\Estate-DCC\Sprint 3\Punters
\D8\Estate-DCC\Sprint 4
\D8\Estate-DCC\Sprint 4\Avatar
\D8\Estate-DCC\Sprint 5
\D8\Estate-DCC\Sprint 5\Avatar
\D8\Estate-DCC\Sprint 5\Pacers
\D8\Estate-DCC\Sprint 6
\D8\Estate-DCC\Sprint 6\Avatar
\D8\Estate-DCC\Sprint 6\Pacers
\D8\Estate-DCC\Sprint 7
\D8\Estate-DCC\Sprint 7\Avatar
\D8\Estate-DCC\Sprint 8
\D8\Estate-DCC\Sprint 8\Avatar
\DBT
\DBT\Hardening
\DBT\Hardening\Avatar
\DBT\Hardening\Punters
\DBT\Hardening\Quasar
\DBT\Hardening\Rainbow
\DBT\Sprint 0
\DBT\Sprint 0\Punters
\DBT\Sprint 0\Quasar
\DBT\Sprint 0\Rainbow
\DBT\Sprint 1
\DBT\Sprint 1\Punters
\DBT\Sprint 1\Quasar
\DBT\Sprint 1\Rainbow
\DBT\Sprint 2
\DBT\Sprint 2\Avatar
\DBT\Sprint 2\Punters
\DBT\Sprint 2\Quasar
\DBT\Sprint 2\Rainbow
\DBT\Sprint 3
\DBT\Sprint 3\Avatar
\DBT\Sprint 3\Punters
\DBT\Sprint 3\Quasar
\DBT\Sprint 3\Rainbow
\DBT\Sprint 4
\DBT\Sprint 4\Avatar
\DBT\Sprint 4\Punters
\DBT\Sprint 4\Quasar
\DBT\Sprint 4\Rainbow
\DBT\Sprint 5
\DBT\Sprint 5\Avatar
\DBT\Sprint 5\Punters
\DBT\Sprint 5\Quasar
\DBT\Sprint 5\Rainbow
\DBT Release
\DBT Release\DBT AandG
\DBT Release\DBT AandG\Sprint 1
\DBT Release\DBT AandG\Sprint 1\Avatar
\DBT Release\DBT AandG\Sprint 1\Pacers
\DBT Release\DBT AandG\Sprint 1\Quasar
\DBT Release\DBT AandG\Sprint 2
\DBT Release\DBT AandG\Sprint 2\Avatar
\DBT Release\DBT AandG\Sprint 2\Pacers
\DBT Release\DBT AandG\Sprint 2\Quasar
\DBT Release\DBT AandG\Sprint 3
\DBT Release\DBT AandG\Sprint 3\Pacers
\DBT Release\DBT AandG\Sprint 3\Quasar
\DBT Release\DBT AandG\Sprint 3\Rainbow
\DBT Release\DBT AandG\Sprint 4
\DBT Release\DBT AandG\Sprint 4\Pacers
\DBT Release\DBT AandG\Sprint 5
\DBT Release\DBT AandG\Sprint 5\Avatar
\DBT Release\DBT AandG\Sprint 5\Pacers
\DBT Release\DBT AandG\Sprint 5\Quasars
\DBT Release\DBT AandG\Sprint 6 - Hardening
\DBT Release\DBT AandG\Sprint 6 - Hardening\Avatar
\DBT Release\DBT AandG\Sprint 6 - Hardening\Pacers
\DBT Release\DBT AandG\Sprint 6 - Hardening\Quasars
\DBT Release\DBT Robustness
\DBT Release\DBT Robustness\Sprint-1
\DBT Release\DBT Robustness\Sprint-1\Elites
\DBT Release\DBT Robustness\Sprint-1\Pacers
\DBT Release\DBT Robustness\Sprint-2
\DBT Release\DBT Robustness\Sprint-2\Elites
\DBT Release\DBT Robustness\Sprint-2\Pacers
\DBT Release\DBT Robustness\Sprint-3
\DBT Release\DBT Robustness\Sprint-3\Elites
\DBT Release\DBT Robustness\Sprint-3\Pacers
\DBT Release\DBT Robustness\Sprint-3\Punters
\DBT Release\DBT Robustness\Sprint-4 (Hardening)
\DBT Release\DBT Robustness\Sprint-4 (Hardening)\Pacers
\DBT Release\DBT1.1
\DBT Release\DBT1.1\Hardening
\DBT Release\DBT1.1\Hardening\Mercurians
\DBT Release\DBT1.1\Hardening\Quasars
\DBT Release\DBT1.1\Hardening\Rainbow
\DBT Release\DBT1.1\Hardening 2
\DBT Release\DBT1.1\Hardening 2\Mercurians
\DBT Release\DBT1.1\Hardening 2\Quasar
\DBT Release\DBT1.1\Sprint 0
\DBT Release\DBT1.1\Sprint 0\Quasars
\DBT Release\DBT1.1\Sprint 1
\DBT Release\DBT1.1\Sprint 1\Punters
\DBT Release\DBT1.1\Sprint 1\Quasars
\DBT Release\DBT1.1\Sprint 10
\DBT Release\DBT1.1\Sprint 10\Rainbow
\DBT Release\DBT1.1\Sprint 2
\DBT Release\DBT1.1\Sprint 2\Punters
\DBT Release\DBT1.1\Sprint 2\Quasars
\DBT Release\DBT1.1\Sprint 2\Rainbow
\DBT Release\DBT1.1\Sprint 3
\DBT Release\DBT1.1\Sprint 3\Punters
\DBT Release\DBT1.1\Sprint 3\Quasars
\DBT Release\DBT1.1\Sprint 3\Rainbow
\DBT Release\DBT1.1\Sprint 4
\DBT Release\DBT1.1\Sprint 4\Avatar
\DBT Release\DBT1.1\Sprint 4\Punters
\DBT Release\DBT1.1\Sprint 4\Quasars
\DBT Release\DBT1.1\Sprint 4\Rainbow
\DBT Release\DBT1.1\Sprint 5
\DBT Release\DBT1.1\Sprint 5\Mercurians
\DBT Release\DBT1.1\Sprint 5\Punters
\DBT Release\DBT1.1\Sprint 5\Quasars
\DBT Release\DBT1.1\Sprint 5\Rainbow
\DBT Release\DBT1.1\Sprint 6
\DBT Release\DBT1.1\Sprint 6\Mercurians
\DBT Release\DBT1.1\Sprint 6\Punters
\DBT Release\DBT1.1\Sprint 6\Quasars
\DBT Release\DBT1.1\Sprint 6\Rainbow
\DBT Release\DBT1.1\Sprint 7
\DBT Release\DBT1.1\Sprint 7\Mercurians
\DBT Release\DBT1.1\Sprint 8
\DBT Release\DBT1.1\Sprint 8\Mercurians
\DBT Release\DBT1.1\Sprint 8\Rainbow
\DBT Release\DBT1.1\Sprint 9
\DBT Release\DBT1.1\Sprint 9\Rainbow
\HDS Phase 2
\HDS Phase 2\Hardening
\HDS Phase 2\Hardening\Mercurians
\HDS Phase 2\Sprint 0
\HDS Phase 2\Sprint 0\Mercurians
\HDS Phase 2\Sprint 1
\HDS Phase 2\Sprint 1\Mercurians
\HDS Phase 2\Sprint 2
\HDS Phase 2\Sprint 2\Mercurians
\HDS Phase 2\Sprint 3
\HDS Phase 2\Sprint 3\Mercurians
\HDS Phase 2\Sprint 4
\HDS Phase 2\Sprint 4\Mercurians
\HDS Phase 2\Sprint 5
\HDS Phase 2\Sprint 5\Mercurians
\HDS Phase 2\Sprint 6
\HDS Phase 2\Sprint 6\Avatar
\HDS Phase 2\Sprint 6\Mercurians
\HDS Phase 2\Sprint 7
\HDS Phase 2\Sprint 7\Avatar
\HDS Phase 2\Sprint 7\Mercurians
\HDS Phase 2\Sprint 8
\HDS Phase 2\Sprint 8\Avatar
\HDS Phase 2\Sprint 8\Mercurians
\International
\International\R14
\International\R14\Sprint 0
\International\R14\Sprint 0\Avatar
\International\R14\Sprint 1
\International\R14\Sprint 1\Avatar
\International\R14\Sprint 10
\International\R14\Sprint 10\Avatar
\International\R14\Sprint 2
\International\R14\Sprint 2\Avatar
\International\R14\Sprint 3
\International\R14\Sprint 3\Avatar
\International\R14\Sprint 4
\International\R14\Sprint 4\Avatar
\International\R14\Sprint 4\GEO
\International\R14\Sprint 5
\International\R14\Sprint 5\Avatar
\International\R14\Sprint 5\Avatar\GEO
\International\R14\Sprint 6
\International\R14\Sprint 6\Avatar
\International\R14\Sprint 6\GEO
\International\R14\Sprint 7
\International\R14\Sprint 7\Avatar
\International\R14\Sprint 7\GEO
\International\R14\Sprint 8
\International\R14\Sprint 8\Avatar
\International\R14\Sprint 9
\International\R14\Sprint 9\Avatar
\International\R15
\International\R15\Sprint 1
\International\R15\Sprint 1\Avatar
\International\R15\Sprint 2
\International\R15\Sprint 2\Avatar
\International\R15\Sprint 3
\International\R15\Sprint 3\Avatar
\International\R15\Sprint 4
\International\R15\Sprint 4\Avatar
\International\R15\Sprint 5
\International\R15\Sprint 5\Avatar
\International\R15\Sprint 6
\International\R15\Sprint 6\Avatar
\International\R15\Sprint 7
\International\R15\Sprint 7\Avatar
\International\R16
\International\R16\Sprint 0
\International\R16\Sprint 0\Punters
\International\R16\Sprint 1
\International\R16\Sprint 1\Punters
\International\R16\Sprint 2
\International\R16\Sprint 2\Punters
\Legal and Marketing
\Legal and Marketing\Hardening
\Legal and Marketing\Hardening\Punters
\Legal and Marketing\Sprint 1
\Legal and Marketing\Sprint 1\Avatar
\Legal and Marketing\Sprint 1\Pacers
\Legal and Marketing\Sprint 1\Punters
\Legal and Marketing\Sprint 2
\Legal and Marketing\Sprint 2\Avatar
\Legal and Marketing\Sprint 2\Pacers
\Legal and Marketing\Sprint 2\Punters
\Legal and Marketing\Sprint 3
\Legal and Marketing\Sprint 3\Avatar
\Legal and Marketing\Sprint 3\Pacers
\Legal and Marketing\Sprint 3\Punters
\Legal and Marketing\Sprint 4
\Legal and Marketing\Sprint 4\Avatar
\NPD_BRAG
\NPD_BRAG\Sprint 1
\NPD_BRAG\Sprint 1\Elites
\NPD_BRAG\Sprint 1\Pacers
\NPD_BRAG\Sprint 1\Punters
\NPD_BRAG\Sprint 2
\NPD_BRAG\Sprint 2\Pacers
\NPD_BRAG\Sprint 2\Punters
\NPD_BRAG\Sprint 3 - Hardening
\NPD_BRAG\Sprint 3 - Hardening\Pacers
\One Core
\One Core\Sprint 1
\One Core\Sprint 1\Pinnacle
\PickingImprovements
\PickingImprovements\Hardening
\PickingImprovements\Sprint 0
\PickingImprovements\Sprint 0\Elites
\PickingImprovements\Sprint 0\Mercurians
\PickingImprovements\Sprint 0\Pinnacle
\PickingImprovements\Sprint 0\Punters
\PickingImprovements\Sprint 1
\PickingImprovements\Sprint 1\Elites
\PickingImprovements\Sprint 1\Mercurians
\PickingImprovements\Sprint 1\Pinnacle
\PickingImprovements\Sprint 1\Punters
\PickingImprovements\Sprint 1\Rainbow
\PickingImprovements\Sprint 2
\PickingImprovements\Sprint 2\Elites
\PickingImprovements\Sprint 2\Mercurians
\PickingImprovements\Sprint 2\Pinnacle
\PickingImprovements\Sprint 3
\PickingImprovements\Sprint 3\Avatar
\PickingImprovements\Sprint 3\Pinnacle
\PickingImprovements\Sprint 4
\PickingImprovements\Sprint 4\Pinnacle
\SDC Mopup
\SDC Mopup\Sprint 3
\SDC Mopup\Sprint 3\Punters
\SDC Mopup\Sprint 4
\SDC Mopup\Sprint 4\Punters
\SIC
\SIC\Phase 1
\SIC\Phase 1\Sprint 1
\SIC\Phase 1\Sprint 1\Avatar
\SIC\Phase 1\Sprint 1\Pinnacle
\SIC\Phase 1\Sprint 1\Quasar
\SIC\Phase 1\Sprint 1\Rainbow
\SIC\Phase 1\Sprint 2
\SIC\Phase 1\Sprint 2\Avatar
\SIC\Phase 1\Sprint 2\Mercurians
\SIC\Phase 1\Sprint 2\Pinnacle
\SIC\Phase 1\Sprint 2\Rainbow
\SIC\Phase 1\Sprint 3
\SIC\Phase 1\Sprint 3\Avatar
\SIC\Phase 1\Sprint 3\Mercurians
\SIC\Phase 1\Sprint 3\Pinnacle
\SIC\Phase 1\Sprint 3\Rainbow
\SIC\Phase 1\Sprint 4
\SIC\Phase 1\Sprint 4\Pinnacle
\SIC\Phase 1\Sprint 4\Rainbow
\SIC\Phase 1\Sprint 5
\SIC\Phase 1\Sprint 5\Mercurians
\SIC\Phase 1\Sprint 5\Pacers
\SIC\Phase 1\Sprint 5\Pinnacle
\SIC\Phase 1\Sprint 5\Rainbow
\SIC\Phase 1\Sprint 6
\SIC\Phase 1\Sprint 6\Mercurians
\SIC\Phase 1\Sprint 6\Pacers
\SIC\Phase 1\Sprint 6\Pinnacle
\SIC\Phase 2
\SOD QF
\SOD QF\Sprint 1
\SOD QF\Sprint 1\Pacers
\SOD QF\Sprint 2
\SOD QF\Sprint 2\Pacers
\SOD QF\Sprint 3
\SOD QF\Sprint 3\Pacers
\SOD QF\Sprint 4
\SOD QF\Sprint 4\Pacers
\XY Phase 2
\XY Phase 2\Sprint 0
\XY Phase 2\Sprint 0\Firebirds
\XY Phase 2\Sprint 1
\XY Phase 2\Sprint 1\Firebirds
\XY Phase 2\Sprint 2
\XY Phase 2\Sprint 2\Firebirds
\XY Phase 2\Sprint 3
\XY Phase 2\Sprint 3\Firebirds
\XY Phase 2\Sprint 4
\XY Phase 2\Sprint 4\Firebirds
\XY Phase 2\Sprint 5
\XY Phase 2\Sprint 5\Firebird
all_VSTS_b92bd3fd_4725_4a6d_aad1_b2a8ae8baf11_System.IterationPath